## CCDF Work Group Recommendations
DATE ACTION TAKEN | WORKGROUP | RECOMMENDATION | ADDITIONAL | FINANCIAL IMPACT | ADMINISTRATIVE OR LEGISLATIVE ACTION REQUIRED | LEGISLATIVE COMMITTEE | PRIORITY LEVEL - IMMEDIATE OR FUTURE | DISCUSSED DATE | ASSIGNMENT / NEXT STEPS | INCLUDE IN FINAL RECOMMENDATION | NOTES
2023-07-10 | Consolidated Housing Plan | Require Regular State Housing Needs Assessments Every Five Years and Incorporate Findings | The state should Require Housing Needs Assessments Every Five Years and Incorporate Findings by setting clear, measurable targets, strategies and funding dissemination priorities aimed at meeting the most critical needs identified in those assessments. | part of process may need additional staff | administrative through DOH or Legislative | Housing | immediate - next consolidated plan 2025 | 2023-06-12 |  | YES 7/10/2023 | review with housing bill passed
2023-07-10 | Consolidated Housing Plan | Tailor Plan to Communities | The Consolidated Plan should be Tailored to Communities, creating clear guidance and measurable targets for affordable housing preservation and development in rural, suburban and urban communities that reflects the attributes unique to each that make housing development ideal or more challenging. | part of process may need additional staff | administrative through DOH or Legislative | Housing | immediate - next consolidated plan 2025 | 2023-06-12 |  | YES 7/10/2023 | review with housing bill passed
2023-07-10 | Consolidated Housing Plan | Identify Opportunities and Incentives for Rehabilitation and Preservation | The Consolidated Plan must Identify Opportunities and Incentives for Rehabilitation and Preservation of existing homes and buildings. Additionally, the Consolidated Plan should incorporate preservation targets for those existing deed restricted units reaching the end of their affordability term. | part of process may need additional staff | administrative through DOH or Legislative | Housing | immediate - next consolidated plan 2025 | 2023-06-12 |  | YES 7/10/2023 | review with housing bill passed
2023-07-10 | Consolidated Housing Plan | Address Housing Quality and Healthy Homes | The Consolidated Plan should include incentives and identification of places where designated funding streams that support rehabilitation can be used to Address Housing Quality and Healthy Homes. | part of process may need additional staff | administrative through DOH or Legislative | Housing | immediate - next consolidated plan 2025 | 2023-06-12 |  | YES 7/10/2023 | review with housing bill passed
2023-07-10 | Consolidated Housing Plan | Expand Evaluation of Prior Performance and Align it with AAP and CAPER | The Consolidated plan should Expand Evaluation of Prior Performance to include a detailed evaluation of performance on the affordable housing goals, actions and metrics consistent with recommendation 1 above. | part of process may need additional staff | administrative through DOH / OPM or Legislative | Housing | immediate - next consolidated plan 2025 | 2023-06-12 |  | YES 7/10/2023 | review with housing bill passed
2023-07-10 | Consolidated Housing Plan | Non-Funding Housing Strategies and Alignment with Outside Actors and Plans | The Consolidated Plan could and should go beyond funding implementation goals and be a better vehicle for housing planning in the state by incorporating Non-Funding Housing Strategies and contemplating outside actors and plans. | need additional staffing | administrative through DOH or Legislative | Housing | immediate - next consolidated plan 2025 | 2023-06-12 |  | YES 7/10/2023 | review with housing bill passed
2023-07-10 | Consolidated Housing Plan | Incorporate Input from People with Lived Expertise | In order to develop housing that is truly representative of the choice and needs of those it is serving, the planning and development of the Consolidated Plan should Incorporate Input from People with Lived Expertise of homelessness and housing insecurity. | compensenation for expertise assistance | administrative through DOH or Legislative | Housing | immediate - next consolidated plan 2025 | 2023-06-12 |  | YES 7/10/2023 | review with housing bill passed
2023-01-09 | State and Muniicpal Plans | Amend Section 16a-27 to eliminate the various mandates that have accumulated over the years and to clarify the breadth and focus of the Plan: | To establish a vision for sustainable development and conservation over the long term. | No | Legislative | P & D | Immediate | 2023-01-09 | Referred to P&D Committee for Bill Submission. HB 6647 - Passed House / No Senate acton | YES 7/10/2023
2023-01-09 | State and Muniicpal Plans | Amend Section 16a-27 to eliminate the various mandates that have accumulated over the years and to clarify the breadth and focus of the Plan: | To set measurable objectives for state investments over five years to encourage appropriate use of physical, natural, social, and fiscal resources. | No | Legislative | P & D | Immediate | 2023-01-09 | Referred to P&D Committee for Bill Submission. HB 6647 - Passed House / No Senate acton | YES 7/10/2023
2023-01-09 | State and Muniicpal Plans | Amend Section 16a-27 to eliminate the various mandates that have accumulated over the years and to clarify the breadth and focus of the Plan: | To encourage coordinated development by directing state resources administered to COGs and municipalities | No | Legislative | P & D | Immediate | 2023-01-09 | Referred to P&D Committee for Bill Submission. HB 6647 - Passed House / No Senate acton | YES 7/10/2023
2023-01-09 | State and Muniicpal Plans | Amend Section 16a-28 to adjust process milestones | Enable more time for OPM to engage with stakeholders prior to submitting a first draft to the Continuing Committee – push to Dec. 1, 2023 (current “first draft” due Sept. 1, 2023) | No | Legislative | P & D | Immediate | 2023-01-09 | Referred to P&D Committee for Bill Submission. HB 6647 - Passed House / No Senate acton | YES 7/10/2023
2023-01-09 | State and Muniicpal Plans | Amend Section 16a-28 to adjust process milestones | Provide more time to publish draft Plan to OPM website – push to May 1, 2024 (current requirement is March 1, 2024) | No | Legislative | P & D | Immediate | 2023-01-09 | Referred to P&D Committee for Bill Submission. HB 6647 - Passed House / No Senate acton | YES 7/10/2023
2023-01-09 | State and Muniicpal Plans | Amend Section 16a-28 to adjust process milestones | Shorten public engagement period from five months to four months – consider changing from “public hearings” to referring the draft plan to COGs and municipalities for feedback | No | Legislative | P & D | Immediate | 2023-01-09 | Referred to P&D Committee for Bill Submission. HB 6647 - Passed House / No Senate acton | YES 7/10/2023
2023-01-09 | State and Muniicpal Plans | Amend Section 16a-28 to adjust process milestones | Shorten time from three months to two months for revisions following public engagement to still meet Dec. 1, 2024 deadline of transmitting next Draft Plan to Continuing Committee | No | Legislative | P & D | Immediate | 2023-01-09 | Referred to P&D Committee for Bill Submission. HB 6647 - Passed House / No Senate acton | YES 7/10/2023
2023-01-09 | State and Muniicpal Plans | Amend Section 16a-28 to adjust process milestones | Maintain requirements for public hearing by the Continuing Committee to conduct a public hearing prior to recommending to the General Assembly | No | Legislative | P & D | Immediate | 2023-01-09 | Referred to P&D Committee for Bill Submission. HB 6647 - Passed House / No Senate acton | YES 7/10/2023
2023-01-09 | State and Muniicpal Plans | Amend Section 16a-28 to adjust process milestones | Require action by the General Assembly on any C&D Plan formally recommended by the Continuing Committee within three months, with inaction constituting an approval | No | Legislative | P & D | Immediate | 2023-01-09 | Referred to P&D Committee for Bill Submission. HB 6647 - Passed House / No Senate acton | YES 7/10/2023
2023-07-10 | State and Muniicpal Plans | Further changes may be warranted as the C&D Plan gets developed, particularly to 16a-35c, Priority Funding Areas/ Locational Guide Map |  | No | Legislative / PA 21-29 | Continuing Committee | Future | 2023-01-09 |  | YES 7/10/2023 | determine how locational mapping is determined
2023-07-10 | Sewerage | Conduct a data driven study of other state and county sewerage programs with a focus on O&ATS |  | Yes | administrative |  |  | 2023-07-10 |  | YES 7/10/2023
2023-07-10 | Sewerage | Development of municipal plans with infrastructure intersections. | Oversight/review of these plans by DEEP and DPH - COGs coordinating or potentially providing oversight | Staff time | administrative |  |  | 2023-07-10 |  | YES 7/10/2023
2023-07-10 | Sewerage | Better coordination between the DEEP and DPH. | State agency actions must be consistent with the State Plan of Conservation and Development (POCD) including the sewer extensions under the purview of DEEP and water extensions under DPH. | Staff time | administrative |  |  | 2023-07-10 |  | YES 7/10/2023
2023-07-10 | Sewerage | Better coordination between the DEEP and DPH | Examine the rationale and clarify jurisdiction and enforcement authority over common ownership systems (7,500 gpd division) | X | Legislatative PA 23-207 Sec 27 | X | 2025-07-01 | 2023-07-10 |  | YES 7/10/2023
2023-07-10 | Sewerage | Better coordination between the DEEP and DPH. | Evaluation of the adequacy of resources for oversight and enforcement of failed systems, review of water pollution control plans and new permits. Develop statewide database system for all agencies | Yes | administrative |  |  | 2023-07-10 |  | YES 7/10/2023 | not to supercede federal requirements
2023-07-10 | Sewerage | Better coordination between municipal, state government and the COGs | Requiring water pollution control authorities to prepare and regularly update water pollution control plans at intervals to be determined | Local cost | legislative | Public Health |  | 2023-07-10 |  | YES 7/10/2023
2023-07-10 | Sewerage | Better coordination between municipal, state government and the COGs | Adding wastewater systems to the required infrastructure identified in municipal plans of conservation and development | No | legislative |  |  | 2023-07-10 |  | YES 7/10/2023
2023-07-10 | Sewerage | Better coordination between municipal, state government and the COGs | Requiring municipal plans of conservation and development and water pollution control plans to be consistent with the state POCD | No | legislative | P & D |  | 2023-07-10 |  | YES 7/10/2023
2023-07-10 | Sewerage | Education program for other treatment systems be explored and/or a testing and study center be implemented similar to those in Massachusetts and Rhode Island. The subcommittee doesn’t deem it necessary, after consultation with DEEP and DPH, to test the viability, technology or systems. However, using perhaps the scientific expertise at UCONN or CASE or potentially partnering with another testing facility such as the one in Barnstable County could be valuable in developing a program for education or training opportunities in collaboration with our state agencies. | education and outreach for municipal and public | consultant/experts needed | admininistrative |  |  | 2023-07-10 |  | YES 7/10/2023
2023-07-10 | Model Codes | Provide funding to engage a consultant or multiple consultants to develop voluntary model code guidelines for municipalities. | tool for municpalities | consultant/experts needed | admininistrative |  | immediate | 2023-06-12 |  | YES 7/10/2023
2023-07-10 | Model Codes | Enhance land use planning capacity at the state level and provide sufficient resources to better integrate statewide objectives and local land use decisions. The Office of Responsible Growth (ORG) within the Office of Policy and Management should develop support and incentives to help improve planning practice in Connecticut, including the adoption of model code guidelines by local governments. |  | none | administrative |  | immediate | 2023-06-12 |  | YES 7/10/2023 | technical planning assistance
2023-07-10 | Model Codes | Facilitate the incorporation of best practices into municipal regulation, standards, and processes. Adoption of best practices, such as model code guidelines, is a challenge in part because local regulation, standards, and processes vary significantly – few practices can be adopted without some legwork translating those practices into a local framework. |  | grant funding | administrative |  | future | 2023-06-12 |  | YES 7/10/2023 | COG Assistance
2023-07-10 | Model Codes | Improve coordination to support effective and efficient plan implementation |  | none | administration |  | immediate | 2023-06-12 |  | YES 7/10/2023 | COG Assistance
2023-07-10 | Affordable Housing Plans | Direct towns, in a specific timetable, to revise their 2021-2022 plans in light of the guidance stated in this report. |  | municipal cost | Legislative / PA 23-137 |  |  | 2023-06-12 |  | YES 7/10/2023
2023-07-10 | Affordable Housing Plans | Specify which board/agency/commission has the responsibility to approve and administer the plan. |  | none | Legislative |  |  | 2023-06-12 |  | YES 7/10/2023
2023-07-10 | Affordable Housing Plans | Consider adopting specific recommendations in this report as action steps and timetables. |  | none | Legislative / PA 21-29 |  |  | 2023-06-12 |  | YES 7/10/2023
2023-07-10 | Affordable Housing Plans | Require each updated report contain a checklist against the criteria stated in § VIII of this report. |  | minimal | Legislative |  |  | 2023-06-12 |  | YES 7/10/2023
2023-07-10 | Affordable Housing Plans | Require the Department of Housing to prepare and publish a model Affordability Plan, to demonstrate best practices for affordable housing administration. Topics could inlcude how to thandle capital improvements; comparability among units; determination of mortgage rates in affordable units for sale; utility cost calculations; and where to go online for median income and fair market rent data. |  | minimal | admininistrative - DOH |  |  | 2023-06-12 |  | YES 7/10/2023